## Main
| Today | Copy this doc and follow the link below for instructions. |  |  | 36.5 | 0 |  |  |  | 14 | 2 | 2 | 3 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2016-10-31 | http://bazald.com/eecs-494/burndown |  |  | Hours | Hours | Hours |  |  | Mon | Wed | Fri | Mon | Wed | Fri | Mon | Mon | Mon | Mon | Mon | Mon | Mon | Mon | Mon | Bug Statuses are used below in the bug area | Bug
# | Rank | Task | Assn | Assist | Est. | Rem. | Worked |  |  | 2016-10-17 | 2016-10-19 | 2016-10-21 | 2016-10-24 | 2016-10-26 | 2016-10-28 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | Detailed Information | Status
Task Assignments | [25 empty] | Reported
7 | 1 | [24 empty] | Verify?
8 |  | General Tasks | [23 empty] | Fixed
9 | 1 | Do research (collect information and compare) | ME |  | 1.5 | 0 | 1.5 |  | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Deferred
10 | 1 | Write up research and analysis | ME |  | 1 | 0 | 1 |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fact of Life
11 | 1 | Plan out basic mechanics | ME |  | 2 | 0 | 3 |  | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Can't Repro
12 | 1 | Justification document | ME |  | 1.5 | 0 | 1.5 |  | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13
14
15
16
17
18
19
20
21 |  | Level Implementation
22 | 1 | Basic Level showcasing dynamics so far | ME |  | 2 | 0 | 1 |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 2 | Tutorial level | ME |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 3 | one or two introductory (more than tutorial) levels | ME |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 3 | one or two full levels showing off the game and mechanics | ME |  | 2 | 0 | 1 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 1 | Ramping up to full levels (introducing added mechanics) | ME |  | 3 | 0 | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27
28
29
30 |  | Main Mecanics Implementation
31 | 1 | Set up 3D space for moving objects | ME |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 1 | Define how object move --> with the mouse? | ME |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | 1 | Define how the world moves --> arrow keys? | ME |  | 1 | 0 | 2 |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | 1 | Define 3 or four interactive objects | ME |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | 1 | Some kind of end and some kind of goal | ME |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 1 | Handle if player falls off screen or needs to restart the level | ME |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39
40
41
42
43
44
45 |  | Aesthetics
46 | 3 | Individual object mechanics aesthetics | ME |  | 3 | 0 | 2 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | 3 | Interative world buttons aesthetics | ME |  | 1 | 0 | 0 |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 3 | World aesthetics | ME |  | 2 | 0 | 1 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | 1 | Start menu and level menu | ME |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | 3 | Set up world sounds | ME |  | 3 | 0 | 2 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | 2 | Game system naviatitions (and menus) | ME |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
Bugs to be Fixed!!! | [24 empty] | Fix Description (if unusual or useful to later generations) | Status
107 | [25 empty] | Reported
108 | [25 empty] | Reported
109 | [25 empty] | Reported
110 | [25 empty] | Reported
111 | [25 empty] | Reported
112 | [25 empty] | Reported
113 | [25 empty] | Reported
114 | [25 empty] | Reported
115 | [25 empty] | Reported
116 | [25 empty] | Reported
117 | [25 empty] | Reported
118 | [25 empty] | Reported
119 | [25 empty] | Reported
120 | [25 empty] | Reported
121 | [25 empty] | Reported
122 | [25 empty] | Reported
123 | [25 empty] | Reported
124 | [25 empty] | Reported
125 | [25 empty] | Reported
126 | [25 empty] | Reported
127 | [25 empty] | Reported
128 | [25 empty] | Reported
129 | [25 empty] | Reported
130 | [25 empty] | Reported
131 | [25 empty] | Reported
132 | [25 empty] | Reported
133 | [25 empty] | Reported
134 | [25 empty] | Reported
135 | [25 empty] | Reported
136 | [25 empty] | Reported
137 | [25 empty] | Reported
138 | [25 empty] | Reported
139 | [25 empty] | Reported
140 | [25 empty] | Reported
141 | [25 empty] | Reported
142 | [25 empty] | Reported
143 | [25 empty] | Reported
144 | [25 empty] | Reported
145 | [25 empty] | Reported
146 | [25 empty] | Reported
147 | [25 empty] | Reported
148 | [25 empty] | Reported
149 | [25 empty] | Reported
150 | [25 empty] | Reported
151 | [25 empty] | Reported
152 | [25 empty] | Reported
153 | [25 empty] | Reported
154 | [25 empty] | Reported
155 | [25 empty] | Reported
156 | [25 empty] | Reported
157 | [25 empty] | Reported
158 | [25 empty] | Reported
159 | [25 empty] | Reported
160 | [25 empty] | Reported
161 | [25 empty] | Reported
162 | [25 empty] | Reported
163 | [25 empty] | Reported
164 | [25 empty] | Reported
165 | [25 empty] | Reported
166 | [25 empty] | Reported
167 | [25 empty] | Reported
168 | [25 empty] | Reported
169 | [25 empty] | Reported
170 | [25 empty] | Reported
171 | [25 empty] | Reported
172 | [25 empty] | Reported
173 | [25 empty] | Reported
174 | [25 empty] | Reported
175 | [25 empty] | Reported
176 | [25 empty] | Reported
177 | [25 empty] | Reported
178 | [25 empty] | Reported
179 | [25 empty] | Reported
180 | [25 empty] | Reported
181 | [25 empty] | Reported
182 | [25 empty] | Reported
183 | [25 empty] | Reported
184 | [25 empty] | Reported
185 | [25 empty] | Reported
186 | [25 empty] | Reported
187 | [25 empty] | Reported
188 | [25 empty] | Reported
189 | [25 empty] | Reported
190 | [25 empty] | Reported
191 | [25 empty] | Reported
192 | [25 empty] | Reported
193 | [25 empty] | Reported
194 | [25 empty] | Reported
195 | [25 empty] | Reported
196 | [25 empty] | Reported
197 | [25 empty] | Reported
198 | [25 empty] | Reported
199 | [25 empty] | Reported
200 | [25 empty] | Reported
201 | [25 empty] | Reported
202 | [25 empty] | Reported
203 | [25 empty] | Reported
204 | [25 empty] | Reported
205 | [25 empty] | Reported
206 | [25 empty] | Reported
207
208
Interpreted Data
210 |  | Days | [6 empty] | 14 | 14 | 12 | 10 | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
211 |  | Optimum | [5 empty] | Line | 36.5 | 36.5 | 31.2857 | 26.0714 | 18.25 | 13.0357 | 7.8214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
212
213 |  | Sum | [6 empty] | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5
214 |  | Rank (and not reduced to 0 after today)
215 |  | Rank 1 - The MOST important | 1 | [5 empty] | 19.5 | 19.5 | 15 | 13 | 8 | 8 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 |  |  | 2 | [5 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
217 |  |  | 3 | [5 empty] | 13 | 13 | 13 | 13 | 13 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
218 |  |  | 4 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 |  | Rank 5 - The LEAST important | 5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220
221 |  | Assigned (Replace these with your team members!)
222 |  | Morgan Erlich | ME |  |  |  |  | ME | 36.5 | 36.5 | 32 | 30 | 25 | 24 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233
234
235 | [7 empty] | DateLine | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5
236

## Daily Scrum
Producer | 2016-10-31 |  | Team Members
Approved | Dates |  | Morgan Erlich
| 2016-10-17 | Mon | PROJECT NOT STARTED YET
| 2016-10-18 | Tue | PROJECT NOT STARTED YET
| 2016-10-19 | Wed | PROJECT NOT STARTED YET
| 2016-10-20 | Thu | "Done: Research for research and analysis document Next: Write research and analysis document Help: -- "
| 2016-10-21 | Fri | "Done: Wrote Research and analysis Next: Sketch 1st level and implement world rotation Help: -- "
| 2016-10-22 | Sat | "Done: World Rotation and Sketched 1st level Next: Ramp implementation Help: -- "
| 2016-10-23 | Sun | "Done: Ramps implemeted Next: Elevators and goal Help: -- "
| 2016-10-24 | Mon | "Done: Elevator and goal (almost done) Next: Refine elevator and goal, and then work on accelorator Help: -- "
| 2016-10-25 | Tue | "Done: Accelorator done and elevator and goal refined Next: Set up tutorial level Help: -- "
| 2016-10-26 | Wed | NA
| 2016-10-27 | Thu | "Done: Tutorial level set up Next: Guidence text boxes, and refine tutorial level Help: -- "
| 2016-10-28 | Fri | "Done: Guidence text boxes, and tutorial level refiened Next: Aesthetics for goal, fix world demensions, and levels introducting new mechanics Help: -- "
| 2016-10-29 | Sat | NA
| 2016-10-30 | Sun | "Done: Aesthetics for goal, fixed world deminsions, 2 levels introducing mechanics done Next: Add one more mechanic, introdcutory level for this mechanic, 2 full levels Help: -- "
| 2016-10-31 | Mon | "Done: Refined game, 2 more full levels, added direction based arroows, level showcasing mechanics done, added sound to game, wrote justification document Next: -- Help: -- "
| 2016-11-01 | Tue
| 2016-11-02 | Wed
| 2016-11-03 | Thu
| 2016-11-04 | Fri
| 2016-11-05 | Sat
| 2016-11-06 | Sun
| 2016-11-07 | Mon